## Slide 1
P R O W E S S
You and Prowess, Better Together
REDCO Rollout to AZAD
SAP SuccessFactors Employee Central
Pre-Requisites, Gap Assessment & Migration Scope
V1.0 | 25th June 2026
Prepared for REDCO • SAP SuccessFactors EC & ECP

## Slide 2
P R O W E S S
Project Objective
REDCO Rollout to AZAD • 25 Jun 2026
2 / 11
01
Onboard REDCO into existing AZAD SuccessFactors Employee Central instance
02
Assess prerequisites before rollout begins
03
Perform AWJ vs AZAD gap analysis
04
Define migration scope for EC & ECP
05
Identify implementation risks and recommendations

## Slide 3
P R O W E S S
Project Pre-Requisites
REDCO Rollout to AZAD • 25 Jun 2026
3 / 11
01
Obtain AWJ system access for analysis
02
Conduct workshop with REDCO HR team
03
Understand business-specific exceptions
04
Create REDCO as a separate Legal Entity in AZAD
05
Provide separate Role-Based Permissions (RBP)
06
Validate integrations and organizational structure

## Slide 4
P R O W E S S
Solution Recommendation
REDCO Rollout to AZAD • 25 Jun 2026
4 / 11
01
Implement REDCO as an independent Legal Entity in AZAD
02
Reuse existing EC configuration wherever applicable
03
Maintain separate security, workflows, and reporting
04
Minimize implementation effort through configuration reuse

## Slide 5
P R O W E S S
AZAD vs AWJ Gap Analysis
REDCO Rollout to AZAD • 25 Jun 2026
5 / 11
Feature | Status | Notes
Business Trip | Similar | Minor field changes
Schooling Allowance | Similar | Minor field changes
Annual Ticket Request | Gap | Not available in AWJ
Miscellaneous Request | Different | Azad: Training Request + Business Card Request
Training Request | Different | Separate request type in AWJ
Exit / Re-entry Visa | Similar | Minor field changes
Letters | Different | Configuration differs between systems
Housing Advance | Similar | Available in both systems
Benefits | Different | Health & wellness, Marriage, Relocation, New Born Gift
Accrual & Leave | Different | AWJ: grade-based monthly; Azad: 22 days flat
Time Tracking | Different | Enabled in Azad; OT manual in AWJ Timesheet
Workflow | Similar | Minor differences only
Other Payments | Gap | Not available in AWJ

## Slide 6
P R O W E S S
Key Functional Differences
REDCO Rollout to AZAD • 25 Jun 2026
6 / 11
01
Benefits configuration differences between AZAD and AWJ
02
Time Tracking enabled in Azad; OT entered manually in AWJ Timesheet
03
Leave policy differences — grade-based in AWJ vs flat 22 days in Azad
04
Workflow simplification required for REDCO onboarding

## Slide 7
P R O W E S S
Migration Scope — Employee Central
REDCO Rollout to AZAD • 25 Jun 2026
7 / 11
Active employees only • * Items require discussion on which events to migrate
01
Personal Information
02
Employment Information
03
Job Information *
04
Compensation *
05
Address
06
Email
07
Phone
08
National ID
09
Passport
10
Dependents
11
Emergency Contacts
12
Bank Information
13
Job Relationships
14
Time Profile
15
Work Schedule
16
Exit & Entry Visa Requests
17
Annual Ticket Requests
18
Leaves

## Slide 8
P R O W E S S
Migration Scope — Employee Central Payroll
REDCO Rollout to AZAD • 25 Jun 2026
8 / 11
01
Payroll Area
02
Payroll Status
03
Basic Pay
04
Recurring Payments
05
One-Time Payments — Business Trip, Schooling Allowance, Training Request, Other Payment, Housing Advance, Health & Wellness, Marriage Allowance, Relocation Allowance, New Born Gift
06
Cost Center
07
Tax Information
08
Bank Details
09
Payroll Control Data

## Slide 9
P R O W E S S
Risks & Mitigation
REDCO Rollout to AZAD • 25 Jun 2026
9 / 11
01
Lack of AWJ access — may delay gap assessment timeline
02
Business process differences — realignment required
03
Workflow redesign — approval chain complexity
04
Time Tracking differences — manual OT gaps in payroll
05
Benefit configuration gaps — custom setup required
06
Data Mapping — field-level validation before migration

## Slide 10
P R O W E S S
Implementation Roadmap
REDCO Rollout to AZAD • 25 Jun 2026
10 / 11
Week 1
Discovery
Week 2
Workshops
Week 3
Gap Analysis
Week 4
Design
Weeks 5–6
Build & Development
Week 7
Testing
Week 8
UAT
Week 9
Go-Live Preparation

## Slide 11
P R O W E S S
You and Prowess, Better Together
Thank You
We look forward to partnering with REDCO on this journey.
Prepared for REDCO • SAP SuccessFactors EC & ECP
V1.0 | 25th June 2026